# SmartSupport AI

Risk Assessment & Mitigation Plan
Stakeholder Analysis

Project 5: Agentic AI Customer Support Platform

# 1. Project Overview

SmartSupport AI is a customer-support platform that uses a Large Language Model (LLM) to answer customer questions, retrieve relevant help articles, perform selected support actions, and transfer complex cases to human agents. The proposed system includes a customer chat widget, conversation and message storage, a knowledge base, support tickets, agent and admin dashboards, analytics, and audit logs.

The proposed technology stack includes ASP.NET Core MVC, Entity Framework Core, ASP.NET Identity, OpenAI API or Azure OpenAI, Semantic Kernel, SignalR, Azure Cognitive Search, Redis, Azure Blob Storage, Chart.js, Bootstrap 5, and Microsoft Azure.

This document focuses on the analysis and planning side of the project. Risk ratings are initial estimates based on the project proposal and should be reviewed by the team as implementation details become clearer.

# 2. Stakeholder Analysis

Stakeholders are people or groups who use the system, operate it, fund it, maintain it, or may be affected by its behavior. Understanding their needs helps the team prioritize requirements and manage risks.

| Stakeholder | Role / Interest | Influence | Impact on Project | Main Needs / Expectations |
| --- | --- | --- | --- | --- |
| Customers / End Users | Ask questions, get accurate answers, check order information, and receive help quickly. | High | High | Simple chat experience; accurate, understandable answers; privacy; clear handoff to a human. |
| Human Support Agents | Handle escalated conversations, manage tickets, review AI summaries, and help customers. | High | High | Useful summaries, clear ticket priorities, access to conversation history, ability to correct AI suggestions. |
| Support Team Lead / Manager | Monitor service quality, workload, escalation rates, and customer satisfaction. | High | Medium–High | Reliable analytics, queue visibility, performance indicators, and consistent workflows. |
| System Administrator | Configure users, roles, prompts, knowledge articles, integrations, and system settings. | High | Medium | Secure admin access, manageable configuration, logs, and operational controls. |
| Project Team / Developers | Design, implement, test, document, and deploy the application. | High | High | Clear scope, stable architecture, test data, API documentation, and realistic milestones. |
| Business / Product Owner | Defines support goals, approves scope, and evaluates whether the system meets business needs. | High | Medium–High | Reduced response time, acceptable operating cost, measurable service quality, and controlled risk. |
| AI / Cloud Service Providers | Provide the external LLM and cloud/search services used by the platform. | Medium | Medium | Valid API configuration, service availability, usage limits, and compliance with provider terms. |
| Security / Privacy Responsible Person | Reviews access controls, sensitive data handling, retention, and auditability. | High | Medium | Least-privilege access, appropriate data retention, protection of personal information, and traceable actions. |

## 2.1 Stakeholder Engagement Plan

| Stakeholder Group | Engagement Approach |
| --- | --- |
| Customers | Collect feedback through short usability tests and a post-chat rating; review confusing or unanswered questions. |
| Support agents | Involve agents in defining escalation rules, ticket statuses, and the information shown in the agent dashboard. |
| Managers / Product owner | Agree on success measures and review a brief progress report at milestones. |
| Administrators | Validate roles, configuration screens, access permissions, and audit-log needs. |
| Development team | Use regular task reviews, code reviews, and integration checks; record decisions and unresolved issues. |
| Security / privacy reviewer | Review data flows, permissions, API-key handling, logging, and retention before deployment. |

# 3. Risk Assessment Method

Each risk is scored using two simple scales: Likelihood and Impact, each from 1 to 5. Risk Score = Likelihood × Impact. The score is used to prioritize mitigation; it is not a statistical prediction.

| Score | Likelihood | Impact |
| --- | --- | --- |
| 1 | Rare | Negligible effect on scope or users |
| 2 | Unlikely | Minor inconvenience or limited rework |
| 3 | Possible | Noticeable disruption or moderate rework |
| 4 | Likely | Major feature, schedule, cost, or user impact |
| 5 | Almost certain | Severe disruption, safety, privacy, or delivery impact |

Priority guide: 1–4 = Low; 5–9 = Medium; 10–16 = High; 17–25 = Critical. The team should reassess scores when controls are implemented or project assumptions change.

# 4. Risk Register and Mitigation Plan

| ID | Risk | L | I | Score / Priority | Mitigation / Response | Owner | Residual Risk* |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | AI generates inaccurate or misleading answers | 4 | 5 | 20 — Critical | Use approved knowledge sources for factual answers; instruct the model to say when it cannot find reliable information; test representative questions; provide feedback and escalation options; monitor low-rated responses. | AI Lead + QA | High |
| R2 | Sensitive customer data is exposed or logged unnecessarily | 3 | 5 | 15 — High | Collect only necessary data; restrict access by role; avoid storing secrets in prompts/logs; define retention rules; protect transport and stored data; review logs for personal data. | Backend Lead + Security Owner | Medium–High |
| R3 | External LLM or cloud service is unavailable or slow | 3 | 4 | 12 — High | Set timeouts and controlled retries; show a helpful fallback message; allow ticket creation or human handoff; monitor service errors and response time. | AI/Cloud Developer | Medium |
| R4 | AI tool performs an incorrect or unauthorized action | 3 | 5 | 15 — High | Allowlist available tools; validate every parameter on the server; enforce user permissions independently of the model; require human approval for sensitive actions such as refunds; log actions. | Backend Lead | Medium |
| R5 | Knowledge base contains outdated or conflicting articles | 3 | 4 | 12 — High | Assign article owners; record review dates; provide an update workflow; test retrieval against known questions; show source references where practical. | Knowledge Base Owner + Support Lead | Medium |
| R6 | Project scope is too large for the available time | 4 | 4 | 16 — High | Define a minimum viable product; prioritize core chat, knowledge search, ticket escalation, and basic dashboard; move optional features such as A/B testing and advanced learning to future work. | Project Manager + Team | Medium |
| R7 | Integration problems between ASP.NET, AI SDK, search, Redis, and SignalR | 4 | 4 | 16 — High | Build a small end-to-end prototype early; define interfaces between layers; pin compatible package versions; test integrations separately; keep a documented fallback for nonessential services. | Technical Lead | Medium |
| R8 | API usage costs exceed the project budget | 3 | 4 | 12 — High | Set provider spending limits and alerts where available; cap input/output length; avoid unnecessary repeated calls; cache suitable common responses; monitor usage during testing. | AI/Cloud Developer + Product Owner | Low–Medium |
| R9 | Unauthorized users access agent or admin features | 3 | 5 | 15 — High | Use ASP.NET Identity roles and authorization policies; apply least privilege; validate permissions on the server; test access-denied cases; protect admin configuration and API credentials. | Backend Lead + QA | Medium |
| R10 | Escalation fails or the human queue is not monitored | 3 | 4 | 12 — High | Define clear escalation triggers; create a ticket if live handoff is unavailable; display ticket status; notify assigned agents; test the full AI-to-human flow. | Support Workflow Owner + Backend Lead | Medium |
| R11 | Conversation history or AI-generated summaries lose important context | 3 | 3 | 9 — Medium | Persist messages reliably; define what a summary must include; let agents inspect the original conversation; test long and multi-turn chats; avoid treating summaries as the sole source of truth. | AI Lead + QA | Low–Medium |
| R12 | Real-time chat updates are lost or duplicated | 3 | 3 | 9 — Medium | Use stable message IDs and server-side persistence; handle reconnects; avoid relying only on SignalR delivery; test disconnection and retry scenarios. | Backend Lead | Low–Medium |
| R13 | Deployment configuration or secrets are incorrect | 3 | 4 | 12 — High | Separate development and production settings; store secrets in environment configuration or a managed secret store; verify deployment settings; run smoke tests after release. | DevOps / Deployment Owner | Low–Medium |
| R14 | Analytics show misleading or incomplete metrics | 3 | 3 | 9 — Medium | Define each metric precisely; calculate metrics from stored events; handle missing feedback explicitly; compare dashboard totals with sample records. | Data/Backend Developer + QA | Low |
| R15 | Team members have unclear ownership or duplicated work | 3 | 3 | 9 — Medium | Assign one owner per feature; document interfaces and deliverables; use a shared task board; review dependencies weekly; integrate work continuously. | Project Manager + Team | Low |

*Residual risk is a preliminary estimate after the proposed controls; it should be confirmed by the team.

# 5. Top Risks Requiring Early Attention

| Priority Area | Why It Matters | Immediate Action |
| --- | --- | --- |
| 1. AI answer quality | The product’s main value depends on trustworthy support answers. A wrong answer can frustrate customers or lead them to take an incorrect action. | Test common and edge-case questions; use retrieval from approved articles; provide a clear human escalation path. |
| 2. Privacy and access control | The system stores conversations and may process personal information. A permissions or logging mistake could expose data. | Design role permissions and data handling early; never rely on the AI model to enforce authorization. |
| 3. Tool/action safety | The AI may request an action such as checking an order or initiating a refund. The server must decide whether the action is valid and permitted. | Validate inputs and permissions in C# services; require approval for high-impact actions; maintain an audit trail. |
| 4. Scope and integration complexity | The proposal includes many technologies and advanced capabilities. Attempting all of them at once creates schedule and integration risks. | Deliver a small end-to-end MVP first, then add features in priority order. |

# 6. Recommended Minimum Viable Product (MVP)

To reduce schedule and integration risk, the team should first aim to demonstrate one complete, reliable workflow rather than every advanced feature in the proposal.

| Step | MVP Capability |
| --- | --- |
| 1 | Customer sends a message and receives an AI response. |
| 2 | The AI searches a small, curated FAQ/knowledge base before answering support questions. |
| 3 | Conversation messages are saved in the database. |
| 4 | The system creates a support ticket and transfers the case when the answer is uncertain or the customer requests a person. |
| 5 | A support agent can view the ticket and conversation summary. |
| 6 | Basic authentication, role-based access, error handling, and audit logging are in place. |

Features such as advanced A/B testing, automatic knowledge-base improvement, sophisticated learning loops, and extensive analytics can be considered after the core workflow is stable.

# 7. Risk Monitoring and Review

| When | Review Activity |
| --- | --- |
| Weekly | Review open risks, changes in likelihood/impact, blocked tasks, and mitigation owners. |
| At each milestone | Re-score the highest risks and verify that planned controls have been implemented and tested. |
| Before deployment | Check authorization, sensitive-data handling, API-key storage, error/fallback behavior, and the escalation workflow. |
| After a demo or user test | Review inaccurate answers, failed searches, abandoned chats, escalation outcomes, and user feedback. |

# 8. Conclusion

The main risks for SmartSupport AI are unreliable AI answers, privacy and authorization failures, unsafe tool execution, dependency on external services, and the complexity of integrating multiple technologies within the project timeline. These risks can be reduced by keeping the initial scope focused, validating every action on the server, grounding answers in approved knowledge, preserving a human handoff, and testing the complete workflow early.

Stakeholder engagement is equally important: customers need understandable and dependable help, agents need a useful escalation workflow, administrators need secure controls, and the project team needs clear ownership and achievable milestones. The risk register should be treated as a living document and updated throughout development.